## BugList
# Bug No | Screen / Function | Bug Detail | From | Status | Dev Feedback
2 | Search | We need to use membershi number, Surname or/and Id number to search a particula member | Patrick | Open
3 | Application status report | We are unable to click on the member to get their information, Error 404 - The page you are looking for might have been removed had its name changed or is temporarily unavailable. | Patrick | Open
4 | How to add, delete and amend a new member? | Still outstanding - link to to send to us (WISA) | Patrick | Open
5 | Membership reports. | All Indivual member information, Resignation reports, Suspension reports, Divison membership reports, Job portal, Member Directory, Active Member list, Postal Address - Active Individual Members, Job protal | Patrick | Open
6 | The link to Member Application and Non member | Still outstanding, we need to have this so that we are aware what to tell members when they apply online, | Patrick | Open
7 | Application status - email notification | I picked up one member has registered today because they appear on the report. Chances of us getting the notifications? | Patrick | Open
8 | Company online application | Currently we register the companies manually, will it be possible to create an online registrations? | Patrick | Open
9 | Pastel and CRM | We update both the CRM system to mach with Pastel, can the new system generate the invoices? | Patrick | Open
10 | Member login details | We want members to reset their own login details should they forget the original ones, | Patrick | Open
11 | Manage user | I want to have a report or Stats showing, the login and off time as well as all the members serviced for a particula day, week, monthly and even yearly, | Patrick | Open
12 | Board reports | The example was sent to Evolutio on 22nd September 2020 | Patrick | Open
13 | Reason for Resignation field for internal purposes | While member are joining and resigning, we need a field that will sho their reasons for resigning | Patrick | Open
14 | Welcome letter and Membership Certificate | Can the member be able to print their own Membership pack and only if they are in good standing? We want the cretificated to include the " From date and To date, eg. 01 January 2021 to 31 December 2021, | Patrick | Open
15 | Upgrade - Associate member to Full member, Member to Fellow | Every year we manually upgrade qualifiying members from Associate to Members guided by the WISA criteria and from Members to Fellow, | Patrick | Open
16 | Admin should be able to add a new member without going through the member sign up portal |  | Sunil | Open
17 | Screen changes required to ensure text and background are clear to user |  | Sunil | Open
18 | Scrollbar not showing up in chrome |  | Sunil | Open
19 | Members should not be able to login from admin login and Admin should not login from Member Portal |  | Sunil | Open
20 | Member profile page showing 404 error |  | Sunil | Open
21 | new application links should not take you to admin portal. It should remain completely outside admin portal |  | Sunil | Open
22 | Emails. Patrick should be copied |  | Sunil | Open
23 | Provide option to delete if users are contacts |  | Sunil | Open
24 | Charts - lists don’t tie up with the Y Axis |  | Aji /Sowmy | Open
25 | Application progress report - date format sometime showing errors |  | Aji /Sowmy | Open
26 | font looks light- needs to be black. Update SASS file |  | Aji /Sowmy | Open
27 | Lables to be updated - Non individual form (new and Edit pages) |  | Aji /Sowmy | Open
28 | My Profile - Admin | Physical Address - Update label City to "Town/City" as in Postal | Aji /Sowmy | Fixed
29 | My Profile - Admin | Update Profile button style - Follow Outline style | Aji /Sowmy | Fixed
30 | Change Password | Update fields to compatible size | Aji /Sowmy | Fixed
31 | Change Password | Update Password button style - Follow Outline style | Aji /Sowmy | Fixed
32 | Side bar - Admin | Spelling - Affliation | Aji /Sowmy | Fixed
33 | Dashboard - Admin | Apply Card background for Page Heading | Aji /Sowmy | Open
34 | Dashboard - Admin | Pie charts not showing any numbers | Aji /Sowmy | Open
35 | Dashboard - Admin | No chart for Occupation % | Aji /Sowmy | Open
36 | Dashboard - Admin | Actual member count is not matching with the chart | Aji /Sowmy | Open
37 | Application Progress Report | Apply Card background for Page Heading | Aji /Sowmy | Open
38 | Add New | Allows multi click and saving duplicate records. | Aji /Sowmy | Open
39 | Add New | "Unknow Error" message when we click Add without any data. | Aji /Sowmy | Open

## Client
# | Bug Desc | Status
1 | Test the system in a smaller resolution. Application Status Report page seems to overflow.
2 | Application status report page -Is font size bigger than other pages
3 | Application Status Report – Add Membercode in page and in excel export
4 | Left sidebar should start minimized by default
5 | Try to implement wizard in application pages
6 | New Member adding -> once user confirms his email, system should ask him to set a password
7 | Member Stats- Report builder needs to be looked at
8 | CRM reports that they currently have needs to be built
9 | Edit Icon – Change it to show. Showing two items as icon seems to be confusing
10 | Search control at the top – Hide it if there is no grid in the page
11 | Search button, if user presses enter, it reloads the whole page, giving illusion as the search is not working
12 | Home page should be simple and in two blocks
13 | Tabs style should change to rectangle tabs instead of links
14 | Notes, subject should be dropdown instead of free text and user should also be able to add attachment to notes
15 | Home Page – Should have provisions to display announcements, newsletter links and events)
16 | Dashboard – Look at them and fix issues.
17 | Try if uploading photos can be built
18 | Notifications on errors, edit update, overall notification for multiple validation fails
19 | Reports that are critical to be built
20 | All Member information report – (Active Members listing emails addresses, Additional contact listing emails, Postal addresses Active Individual members, Postal addresses Additional contact)
21 | All Non-Individual information report – (Postal addresses: Active company members and Active mailing list emails
22 | Active division membership reports
23 | Dashboard – I send you an example of the report I will normally share with our board.
24 | Job Portal
25 | Export member balances and provide option to import member balances (Patrick: I will be exporting the individual and non-individual balances and send it through to Regan so that he can update his system and re-send it back to me for Importing on CRM. This is done on a weekly basis and will appreciate if it can be given a priority.
26 | Please note that Membership department has three staff members (i.e. I, Evelyn Ramphomane and Talent Khumalo.
27 | I want to have full access (read and write) to the system since I am the primary custodian of the system.
28 | Evelyn and Talent are membership administrators and access to read and edit/write should be a requirement.
29 | Melissa can be given access to view the reports but no access to edit.
30 | The rest of the staff can have access to view ONLY.
31 | The application forms of the Individual, Professional and Organizations must be re-looked at when it comes to the headings (i.e. preferences and Register) | Fixed
32 | Please replace preferences with the word “Additional information” as it does not sound right to call a disability as preference.
33 | Remove “Declaration words and the tick box” from all the pages.
34 | Remove “Register” on the application and it must be added under “Documents” with the attached document I sent yesterday.
35 | Under the above wording, (i.e. of the attached document” the WISA banking details can be added and just below please add “Register” for the completion of the application.